## Instructions
Instructions | Enter your team name as specified in the cell below. When doing cross-team acceptance testing, enter the name for the testing group. Fill-in the Test Plan worksheet with all the remaining User Stories in your Product Backlog. Since Product acceptance is from the perspective of the end-user, only add User Stories that pertain to the Owner or Buyer and do not include User Stories specifically for the REST API service (e.g. AS a developer...). As your user stories are refined, add the acceptance criteria for each user story. Use a separate worksheet to provide any specific test case data that the tester needs to use. As tests are performed in each sprint, indicate Pass/Fail. Note that there are separate columns for each sprint. The tester should add initials and a date in the comments column. If the test failed, the tester is required to add additional information about the failure. The status cell will color code based on the test results. The comments cell will color code when a test result exists but no information is entered. Save this test plan with a name formatted as "term-swen-261-sec-letter name", e.g. 2171-swen-261-10-a Speedy Racers.xslx. Submit this file per the instructions specified for the sprint submissions and cross-team testing.
Team Name | Your team name as "term-swen-261-sec-letter name", e.g. 2171-swen-261-10-a Speedy Racers
Testing Team Name | fill in when doing cross-team testing

## Test Plan
User Story | Acceptance Criterion | Sprint 2 | Tester initials; date; comments (required if test failed) | Sprint 3 | Tester initials; date; comments (required if test failed)
As a customer I want to see a list of products so that I choose what to purchase. | Given that I am on the e-store site when I am not on the Products page then I must see a means to navigate to the Products page. | Fail | T.G; 11-04-22; Comments: A customer that is on the e-store site is only able to view the products available to be purchased once they are logged in, there isn't a dedicated Product listing page for everyone to view. There isn't a dedicated products page. | Pass
As a customer I want to see a naviagation in order to swiftly traverse through the e-store | Given that I am on the e-store site then I must see a means to navigate through to a log in, signup, or about page. | Pass | T.G; 11-04-22; Comments: A customer is able to traverse through the e-store via the navigation bar to log in, sign up or see the about us page. | Pass
As a customer I want to see a list of products so that I choose what to purchase. | Given that I am not on the Products page when I choose the Products page then I am taken to the Products page. | Fail | T.G; 11-04-22; Comments: A user is only able to go view Products once they are logged in, there isn't a dedicated products page. | Pass
As a customer I want to see a list of products and a short description about each product | Given that I am on the products page when there are products in the inventory then I see each product and short description. | Pass | T.G; 11-04-22; Comments: A product is showcased with minimal information at the beginning and once you click on said product, information about the clicked product will be displayed on a different page. | Pass
As a customer I want the ability to add a product to my shopping cart. | Given that I am on the products page when there are products in the inventory then I see a means to add each product to my shopping cart. | Pass | T.G; 11-04-22; Comments: When a customer is viewing a list of products, they are able to click on a product, see more information about the product and then add it to a shopping cart. | Pass
As a Owner I want the ability to add a new product to my e-store | Given that I am the admin then I see a means to add a new product to my e-store. | Pass | T.G; 11-04-22; Comments: When the Owner wishes to add a new product to their e-store, there is an "add product" button to do so. | Pass
As a Owner I want the ability to update an existing product in my e-store | Given that I am the admin then I see a means to update an existing product in my e-store. | Pass | T.G; 11-04-22; Comments: When the Owner wishes to update an existing product in their e-store all they have to do is click on an existing product and there are input fields for each attribute of a product to edit said product. | Pass
As a Owner I want the ability to delete an existing product in my e-store | Given that I am the admin then I see a means to delete an existing product in my e-store | Pass | T.G; 11-04-22; Comments: When the owner wishes to delete an existing product in their e-store all they have to do is click an existing product and click on the "Delete This Product" button to remove an existing product. | Pass
As a user I want the ability to view product reviews | Given that I am a customer then I see a means to view a review for a product | Pass | T.G; 11-07-22; Comments: When a customer is viewing a product then they should also be able to see a review about it | Pass
As a customer I want the ability to go back to a previous page | Given that I am a customer then I see a means to go back to a page I was on previously | Pass | T.G; 11-07-22; Comments: A customer is able to traverse through the e-store via the navigation bar to log in, sign up or see the about us page. | Pass
As a customer I want the ability to go to a signup page, if I don't have an existing account | Given that I am a customer then I see a means to create an account | Pass | T.G; 11-07-22; Comments: A customer is able to create an account via the navigation bar "Sign Up" or click the button at the very bottom of the "Login" which says "Create An Account" which will redirect the customer to the "Sign Up" page. | Pass